## Sheet1
|  | Messions | Eng.
2021-12-14 | 1 | Design select_db.php file | S+R | problem | Other : | update
| 2 | Check DataBase tables and relations | N | todo |  | delete
| 3 | Code create_db.php & drop_db.php file | M | in-progress
| 4 | Code sql_queries.php | N
| 5 | Code select_db.php file | M | done
| 6 | Code create_backup.php script file | M | next-days
| 7 | Code restore_backup.php script file | M
| 8 | Design open_box_account.php | S
| 9 | Code open_box_account.php | M
| 10 | Design create_account.php file | R
| 11 | Design create_category.php file | R
2021-12-15 | 12 | Code create_account.php file | M
| 13 | Code create_category.php file | M
| 14 | Design create_item.php file
| 15 | Code create_item.php file
| 16 | Design accounts.php file
| 17 | Code accounts.php file
| 18 | Design items.php file
| 19 | Code items.php file
| 20 | Design bills.php file | S
2021-12-16 | 21 | Code bills.php file
| 22 | Code printing functions
| 23 | Design bond_in.php file
| 24 | Code bond_in.php file
| 25 | Design bond_out.php file
| 26 | Code bond_out.php file
| 27 | make test data to insert into DB
| 28 | insert test data in DB
| 29 | Design movement_com.php file
2021-12-18 | 30 | Code movement_com.php file
| 31 | Code printing buttons
| 32 | Design movement_item.php file
| 33 | Code movement_item.php file
| 34 | Design setting.php file
| 35 | Code setting.php file
| 36 | Test All App
| 37 | Style pages
38
39
40
41
Note on C2: Author: form with table to select the databases those user created
Note on C3: Author: choose what tables from souq database, create design, make relations
Note on C4: Author: script : after click a button from select_db form it will take the name fom input to create a database
Note on C6: Author: script : make action to select the DB that choosed from select_db file and alter setting file
Note on C7: Author: make function to backup current database with name
Note on C8: Author: make function to restore the backup database from PC
Note on C9: Author: contain form with the oppening fund for COM and button
Note on C10: Author: add fund to database from the form
Note on C11: Author: form contain account details and address and fund input fields
Note on C12: Author: form contain category input fields